## GanttChart
| Strategic Change Management Programme - Start Date |  | 2024-10-01 | Date | 2025-01-16 |  |  | 2024 | [6 empty] | 2025 | [23 empty] | 2026
| Owner |  | Project Mgr | Ver | 6 |  |  | O |  |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D
 | time axis 2024-10-01 to 2027-01-04
No | Task - See CMP for details | Pty | Task Lead | Task support | Start | End | %
M | Milestones
M1 | Vote on motions | 1 | CEO |  | 2025-03-01 | 2025-05-15 | 0%
M2 | Conference | 1 | CEO |  | 2025-05-15 | 2025-05-30 | 0%
A | Administration
A1 | Produce and approve Change Management Plan | 1 | NBT Chair | STC, PM | 2024-10-01 | 2024-12-14 | 100%
A2 | Produce Comms campaign doc, approve and deliver | 1 | HO Manager | CEO, PM | 2025-01-06 | 2026-12-12 | 20%
A3 | Produce Motions for Conference | 1 | STC Chair | CEO | 2025-01-08 | 2025-02-10 | 20%
A4 | Review post conference output | 3 | STC Chair |  | 2025-06-01 | 2025-07-01 | 0%
A5 | Review constitution for changes | 2 | SIWG Chair |  | 2025-07-01 | 2025-12-12 | 0%
A6 | ToR for Strategic Implementation WG and implement | 2 | NBT Chair | SIWG | 2025-06-01 | 2025-07-01 | 0%
P1 | Organisational reviews and change
P1A | Head Office | 1 | PM | Ind Auditor | 2025-01-10 | 2025-02-15 | 0%
P1B | Areas | 1 | STC Chair | Area Chairs | 2025-04-15 | 2025-08-15 | 0%
P1C | Branches | 2 | Area Secs | HO Manager | 2025-05-15 | 2025-10-15 | 0%
P1D | NBT | 1 | NBT Chair | CEO, PM, Past NBT member | 2025-02-15 | 2025-09-15 | 0%
P1E1 | RBLS Culture - one team | 1 | NBT Chair | PM | 2025-01-15 | 2026-12-15 | 10%
P1E2 | RBLS Culture - Branch conversion to SCIO | 3 | CEO | Area Chairs & Secs | 2025-09-15 | 2027-09-15 | 0%
P1E3 | RBLS Culture - Club FCA registration and model rule book | 2 | Club Chairs | Area Chairs & Secs | 2025-04-15 | 2026-09-15 | 0%
P1F | Other Veterans Charities | 1 | CEO |  | 2025-01-15 | 2025-04-15 | 0%
P1GV | Change | 2 | STC Chair | CEO, PM | 2025-09-15 | 2025-12-15 | 0%
P1HQ | Complaints System | 1 | NBT Chair | CEO, HO Manager | 2024-10-05 | 2025-02-15 | 95%
P1IQ | Project Manager appt | 1 | CEO |  | 2024-11-20 | 2024-12-14 | 100%
P2 | Head Office cost reductions
P2A | Conference review and change | 1 | CEO |  | 2024-10-15 | 2025-05-15 | 20%
P2B | Volunteer support to Head Office | 3 | CEO |  | 2025-02-15 | 2025-11-15 | 0%
P2CQ | Digitisation | 1 | HO Manager | Area & Branch Secs | 2024-11-15 | 2025-09-15 | 20%
P3 | Area Funding
P3AV | Review and agree Area Funding for next 1 to 2 years | 1 | STC Chair | PM | 2024-12-01 | 2025-02-01 | 10%
P3BV | Produce and agree process to request funding | 1 | STC Chair | PM | 2024-12-01 | 2025-02-01 | 0%
P3CV | Produce and agree process to return unused funding | 1 | STC Chair | PM | 2024-12-01 | 2025-02-01 | 0%
P4 | Income opportunities |  |  |  |  | -
P4AV | Capitation increase | 1 | STC Chair | NBT | 2024-11-15 | 2025-02-15 | 40%
P4B | Grant Funding, sponsorship | 1 | CEO | PM | 2025-02-15 | 2026-07-15 | 0%
P4C | Fundraising - Branch and Area level for Head Office | 1 | STC Chair | NBT | 2025-02-15 | 2026-10-15 | 0%
P4DQ | Gift Aid - Guidance | 1 | HO Accounts |  | 2024-11-15 | 2025-02-15 | 70%
P4DQ | Gift Aid - Encourage take up | 1 | HO Accounts | Area & Branch Secs | 2024-11-30 | 2025-10-15 | 20%
P4DQ | Gift Aid - Advertise | 1 | HO Accounts | HO Events | 2024-11-30 | 2026-03-15 | 20%
P4E | Merchandise | 3 | HO Events | Area & Branch Secs | 2025-02-15 | 2026-02-15 | 0%
P5 | Better PR, Marketing, Image, Membership
P5A | Communications guidance, training, campaigns | 2 | CEO | PM | 2025-02-15 | 2025-11-15 | 5%
P5B | Branding - guidelines, décor | 3 | HO Manager | Area & Branch Chairs | 2024-12-15 | 2025-09-15 | 50%
P5C | Social Media | 1 | HO Events | Area & Branch Secs | 2024-11-15 | 2025-11-15 | 0%
P5D | RBLS Web Site | 2 | HO Events | PM | 2024-12-15 | 2025-07-15 | 20%
P5E | Communications - technology - smart phone App | 3 | HO Events | PM | 2024-12-15 | 2026-04-15 | 5%
P5F1 | Image - Strategic Operational Policy | 1 | NBT Chair | CEO | 2025-02-15 | 2025-05-15 | 10%
P5F2 | Image - Remembrance events | 3 | NBT Chair |  | 2025-05-15 | 2026-12-01 | 0%
P5F3 | Image - Branch Clubs modernisation | 2 | Branch Chairs | Area Chairs & Secs | 2025-05-15 | 2027-03-15 | 20%
P6 | Membership specific activities
P6A | Major cities and National Branch | 3 | HO Manager | STC Chair | 2025-02-15 | 2027-03-15 | 10%
P6B | Non Ex Service members & Service leavers | 2 | HO Manager | Area Chairs | 2025-02-15 | 2025-12-15 | 0%
P6C | Making the joining process more efficient | 3 | HO Memb Mgr |  | 2025-01-15 | 2026-09-15 | 0%
P6D | Legion in the community - Creation of Common Interest Branches | 3 | NBT Chair | NBT, CEO, Riders | 2025-01-15 | 2025-12-15 | 0%
P6E1 | Legion in the community - Branch engagement | 2 | Branch Chairs | Area Chairs & Secs | 2025-02-15 | 2025-12-15 | 0%
P6E2 | Legion in the community - Canadian experience | 3 | Area Secs | HO Manager | 2025-02-15 | 2025-09-15 | 0%
P6E3 | Legion in the community - Uniformed youth organisations | 2 | HO Events |  | 2025-02-15 | 2026-06-01 | 0%
P6E4 | Legion in the community - Literature | 2 | HO Manager |  | 2024-11-15 | 2025-04-15 | 50%
P7 | Guidance to Branches |  |  |  |  | -
P7A | Branch Handbook | 2 | HO Manager | CEO | 2025-01-10 | 2025-08-15 | 80%
P7B | "How to" Guides | 2 | HO Manager |  | 2025-01-10 | 2025-08-15 | 0%
Note on A4: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B4: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C4: Priority
Note on D4: Task Lead Enter the name of the Task Lead in this column.
Note on E4: Task Support Enter the names of those who are essential to support completion of this task
Note on F4: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G4: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.

## Drop down menus
Task Lead & Support | Task Support | PTY
NBT Chair | NBT Chair | 1
STC Chair | NBT | 2
SIWG Chair | STC Chair | 3
CEO | STC
HO Manager | SIWG Chair
HO Accounts | SIWG
HO Events | CEO
HO Memb Mgr | HO Manager
PM | HO Accounts
Area Chairs | HO Events
Area Secs | HO Memb Mgr
Branch Chairs | PM
Club Chairs | Area Chairs
Branch Secs | Area Secs
Area Chairs & Secs
Area Executives
Branch Chairs
Branch Secs
Branch Chairs & Secs
Club Chairs
Area & Branch Chairs
Area & Branch Secs
NBT, CEO, Riders
STC, PM
Ind Auditor
PM, HO Manager
CEO, PM, Past NBT member
CEO, HO Manager
CEO, PM

## Help
Help
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos of the Pro Version on Vertex42.com
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
| • Define the task start date and duration (days) by editing the light green cells. | Input Cell
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Help improve Excel by voting on a suggestion to fix this problem.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2018 Vertex42 LLC
Note on C16: This is an example comment.